Research Proposal

Title: Interpretable Machine Learning for Predicting Recurrence in Soft Tissue Sarcoma Using Structured Clinical Data

1. Introduction
Soft tissue sarcoma (STS) encompasses a rare and heterogeneous group of malignancies that account for less than 1% of adult cancers. The recurrence of STS poses significant challenges for long-term patient outcomes and requires precise risk stratification. While machine learning (ML) has demonstrated potential in improving prognostic modeling, most existing studies employ black-box models or rely heavily on imaging data, limiting interpretability and practical clinical adoption. This proposal outlines a study that leverages structured clinical data to develop interpretable ML models for recurrence prediction, aiming to support transparent and ethical clinical decision-making.

2. Project Background
Machine learning applications in oncology have expanded rapidly, particularly in image analysis and outcome prediction. However, the literature indicates a notable gap in ML models that prioritize interpretability and clinical relevance using structured clinical data. Studies such as Xu et al. (2023) and Italiano et al. (2024) explore prediction using EHR data but often lack focus on interpretability and site-specific context. In contrast, this project emphasizes explainable AI (XAI) frameworks (e.g., SHAP, LIME) and real-world, single-institution data, enabling tailored risk prediction and improving model transparency. Furthermore, this project addresses class imbalance—a common issue in recurrence prediction—using resampling and appropriate evaluation metrics like AUPRC and MCC.

3. Project Aims and Objectives
The primary aim of this study is to develop an interpretable machine learning model to predict recurrence in soft tissue sarcoma patients using structured clinical data from a single center.

Objectives:

- To identify and preprocess relevant clinical features including tumor site, histology, demographics, and treatment type.

- To compare interpretable models (e.g., logistic regression, decision trees) with more complex models (e.g., random forests).

- To apply SHAP and LIME to explain model predictions.

- To address class imbalance using SMOTE and appropriate metrics.

- To ensure models are clinically interpretable, ethically sound, and applicable in real-world settings.

4. Expected Research Contribution
This research contributes to both the clinical oncology and ML communities by:

- Developing interpretable recurrence prediction models tailored for STS.

- Demonstrating the value of structured clinical data in place of imaging/genomic data.

- Establishing best practices for handling imbalance and enhancing transparency in rare cancer prediction.

- Providing a practical ML pipeline that clinicians can adopt in decision support systems.

- Offering a methodological template for future research in rare cancers using accessible data and explainable models.

5. Research Programme
The project will proceed in the following stages:

Stage 1: Literature Review

- Review existing ML applications in STS and interpretability tools (Month 1–2).

- Compile related works from clinical oncology and AI ethics literature.

Stage 2: Data Collection and Preprocessing

- Obtain anonymized structured clinical data.

- Perform data quality checks, normalization, and feature engineering (Month 2–3).

- Address missing values and categorical encoding strategies.

Stage 3: Model Development and Training

- Implement baseline models: logistic regression and decision trees.

- Explore random forests and ensemble techniques as secondary models.

- Use cross-validation for robust performance estimation (Month 3–4).

Stage 4: Model Interpretation and Evaluation

- Apply SHAP and LIME to assess model transparency.

- Evaluate models using AUPRC, MCC, PR curves, and traditional metrics (Month 5).

Stage 5: Final Analysis and Reporting

- Synthesize findings and interpret clinical implications.

- Draft and revise dissertation.

- Prepare oral presentation and defense materials (Month 6).

6. Deliverables
The project will result in a cleaned and preprocessed dataset suitable for machine learning analysis. It will also produce a set of trained and validated machine learning models aimed at predicting recurrence in soft tissue sarcoma patients. Interpretability will be supported by SHAP and LIME visual outputs, helping to explain the model predictions. A written analytical summary will detail the most important clinical features identified by the models. These outcomes will be compiled into a comprehensive dissertation document, accompanied by a formal presentation for assessment.
7. Resources Required
This research will require access to anonymized structured clinical data from a medical institution. It will be conducted using Python programming tools within a suitable environment such as Jupyter, Google Colab, or Anaconda. Core libraries like scikit-learn, pandas, SHAP, LIME, and imbalanced-learn will be utilized for model development and analysis. Regular guidance from the academic supervisor and technical mentors will be necessary. Additionally, ethics approval and adherence to institutional data governance protocols will be mandatory for data handling.
8. Risks

| Risk | Likelihood | Impact | Mitigation Plan |
| --- | --- | --- | --- |
| Data access delay | Medium | High | Apply for data access and ethics approval as early as possible. |
| Small sample size | High | Medium | Use feature selection, regularization, and few-shot learning. |
| Class imbalance | High | Medium | Use SMOTE and robust evaluation metrics (AUPRC, MCC). |
| Model interpretability vs. accuracy | Medium | Medium | Compare simple vs. complex models and justify trade-offs. |
| Technical limitations with tools | Low | Low | Use well-documented Python libraries and maintain backup systems. |

9. Ethical Issues
The study will involve the use of retrospective, anonymized patient data, thereby minimizing risks to privacy and confidentiality. Formal approval will be sought from an institutional review board (IRB) prior to commencing the data analysis phase. To ensure the integrity of outcomes, models will not be implemented in clinical settings until proper validation and regulatory clearance are achieved. Ethical communication will include clearly stating the limitations of predictive models to avoid misinterpretation or overreliance in a clinical context.
10. References
Chen, H. et al. (2023) 'Radiomics and artificial intelligence for soft-tissue sarcomas', European Journal of Radiology, 162, p.110728.
Italiano, A. et al. (2024) 'Artificial intelligence for STS survival prediction', Annals of Oncology, 35(Suppl_2), pp.ii123–ii130.
Xu, S. et al. (2023) 'Machine learning predicts recurrence in soft tissue sarcoma', JCO Clinical Cancer Informatics, 7, e2300012.
Zhuang, Y. et al. (2022) 'Imbalance learning for MRT1WI STS classification', Frontiers in Oncology, 12, 941707.
Rieke, N. et al. (2020) 'The future of digital health with federated learning', npj Digital Medicine, 3(1), pp.1–7.
Navarro, F. et al. (2021) 'Deep-learning tumor grading in STS patients using MRI', Cancers, 13(12), p.2866.
Miller, B.J. et al. (2024) 'NLP algorithm for myxofibrosarcoma detection', Clinical Orthopaedics and Related Research.

Appendix: Gantt Chart
[Attach Gantt chart showing timeline across 6 months for literature review, data preprocessing, model development, evaluation, and reporting.]

Font: Size 10; Style: Calibri or Arial as per submission guidelines.